AT&T Internet Air

Product Roadmap & Release Plan

5G Home Internet — Consumer Division

| Classification: Confidential | Division: Consumer Broadband | Date: June 2025 | Version: 2.1 |
| --- | --- | --- | --- |

# 1. Executive Summary

AT&T Internet Air is the company's flagship Fixed Wireless Access (FWA) product, delivering 5G-powered home internet service without the need for trenching or fiber installation. As of Q2 2025, Internet Air has achieved 2.3 million subscribers nationwide, with a monthly net add run-rate exceeding 150,000.

This document covers the 12-month product roadmap through Q2 2026 and the detailed release plan for Internet Air 2.0, which bundles a self-install gateway redesign with Wi-Fi 7 (802.11be) support for GA in Q4 2025. The release is the most significant platform upgrade since the product's 2022 launch, projected to reduce truck-roll costs by $38M annually and improve average throughput to 400 Mbps.

# 2. Vision / North Star

"Make AT&T Internet Air the most frictionless broadband experience in America — self-installs in under 10 minutes, Wi-Fi 7 performance in every room, and a network that continuously self-optimizes so customers never call support."

# 3. Strategic Themes

## Theme 1 — Zero-Touch Customer Onboarding

Eliminate truck rolls and call center intervention for the standard install journey. The new AirGateway 7 hardware ships pre-provisioned with customer-specific RF profiles. The companion app guides customers through placement optimization using 5G signal telemetry, achieving SIQ (Signal IQ) scores before activating service.

## Theme 2 — Wi-Fi 7 Whole-Home Performance

The move to 802.11be (Wi-Fi 7) unlocks multi-link operation (MLO) across 6 GHz, 5 GHz, and 2.4 GHz bands simultaneously. With 4K QAM and up to 320 MHz channel width on 6 GHz, peak throughput in ideal conditions reaches 5.8 Gbps. All existing Internet Air subscribers will receive a hardware upgrade path at no cost in 2026.

## Theme 3 — Proactive Network Assurance

Deploy a cloud-based AI ops layer that monitors gateway telemetry in real time, pre-emptively issues firmware patches, and auto-switches bands when interference is detected. Goal: reduce inbound CARE contacts by 30% by reducing self-inflicted network events.

## Theme 4 — 5G Advanced Capacity Expansion

Coordinate with AT&T network engineering to prioritize FWA-allocated spectrum bands (C-band 3.45 GHz, 2.5 GHz) in the 50 metros with highest Internet Air subscriber density. Unlock mmWave as a secondary carrier aggregation band in urban MDU deployments.

# 4. Roadmap Timeline

| Initiative | Q3 2025 | Q4 2025 | Q1 2026 | Q2 2026 |
| --- | --- | --- | --- | --- |
| AirGateway 7 Hardware (Wi-Fi 7) | Beta | GA | Scale |  |
| Self-Install App v3 | Dev Complete | GA |  |  |
| AI Network Assurance | Alpha | Beta | GA |  |
| mmWave CA (Urban MDU) |  | Pilot | Beta | GA |
| 5G Advanced Spectrum Refarming |  | Planning | Deploy | Complete |
| Whole-Home Wi-Fi 7 Mesh Extender |  |  | Beta | GA |

# 5. Key Initiatives

## 5.1 AirGateway 7 (Wi-Fi 7 Gateway Hardware)

- Hardware partner: Nokia Bell Labs AX7200 platform; AT&T custom firmware

- 802.11be (Wi-Fi 7) with MLO: 2.4 / 5 / 6 GHz simultaneous operation

- Integrated 5G Sub-6 modem: C-band + n41 carrier aggregation

- App-driven placement guidance: signal heatmap rendered in AR overlay

- Auto-provisioning: gateway reads SIM, pulls customer profile, activates in < 4 min

## 5.2 Self-Install App v3

- iOS and Android; redesigned UX reducing install steps from 14 to 7

- Live Signal IQ meter with placement coaching — reduces sub-optimal installs by 45%

- In-app speed test + troubleshooting flow eliminates Tier-1 support calls for common issues

- Supports Spanish, Portuguese, Vietnamese, Mandarin at launch

## 5.3 AI Network Assurance

- Real-time telemetry ingest: 85+ metrics per gateway per minute

- ML model flags degradation 4 hours before customer-impacting event

- Auto-remediation: band steering, TX power adjustment, firmware micro-patch

- Target: 30% reduction in CARE contacts from network-related tickets

# 6. Success Metrics

| Metric | Baseline (Q2 2025) | Target | Timeframe | Owner |
| --- | --- | --- | --- | --- |
| Self-install success rate | 72% | 92% | Q4 2025 | Product |
| Avg install time (min) | 28 min | < 10 min | Q4 2025 | Eng |
| Median dl throughput | 180 Mbps | > 400 Mbps | Q1 2026 | Network |
| Monthly CARE contacts / sub | 0.18 | < 0.12 | Q2 2026 | Ops |
| NPS (Home Internet) | 32 | > 50 | Q2 2026 | CX |
| Monthly net adds | 150K | 250K | Q2 2026 | Sales |

PART B — RELEASE PLAN

Internet Air 2.0: Self-Install + Wi-Fi 7

# 7. Release Overview

| Release Name | Internet Air 2.0 — Self-Install + Wi-Fi 7 |
| --- | --- |
| Version | GW-FW 2.0.0 / App v3.0.0 |
| Target GA Date | November 18, 2025 |
| Release Type | Major (Hardware + Firmware + App) |
| Release Manager | Consumer Broadband PM Team |
| Exec Sponsor | SVP, Consumer Broadband Products |

# 8. Release Scope

| IN SCOPE | OUT OF SCOPE (Deferred to 2.1+) |
| --- | --- |
| - AirGateway 7 hardware (Wi-Fi 7 + 5G C-band/n41 CA) - Self-Install App v3.0 (iOS 16+, Android 12+) - Signal IQ placement engine (AR guidance) - Auto-provisioning: < 4 min gateway activation - In-app speed test and self-help troubleshooting - Multi-language support (ES, PT, VI, ZH) - Remote firmware OTA update mechanism | - Wi-Fi 7 mesh extender hardware (Q1 2026) - AI Network Assurance (separate release) - mmWave carrier aggregation (Urban MDU 2026) - Business / SMB tier support - Legacy AirGateway 5 hardware upgrade path - Parental controls advanced scheduling |

# 9. Release Timeline

| Phase | Date | Owner | Exit Criteria |
| --- | --- | --- | --- |
| Feature Freeze | Sep 5, 2025 | Eng / PM | All P0/P1 features merged, no open blockers |
| Dev Complete | Sep 26, 2025 | Engineering | Unit + integration tests green, code review done |
| Internal Beta (AT&T Employees) | Oct 6 – Oct 24, 2025 | QA + Product | 500 devices, < 5 Sev-2 bugs open, NPS > 40 |
| Closed Beta (Invite Customers) | Oct 27 – Nov 7, 2025 | Product + CX | 2,000 devices, crash-free rate >= 99.5% |
| Canary (1% GA traffic) | Nov 10 – Nov 14, 2025 | Eng + Ops | No Sev-1, CARE contact rate < 0.15/sub |
| GA Rollout (staged) | Nov 18 – Dec 5, 2025 | Release Mgmt | 100% new hardware orders, OTA to existing base |

# 10. Rollout Strategy

## Hardware Rollout

AirGateway 7 hardware ships to new subscribers starting November 18. Existing AirGateway 5/6 subscribers are not migrated in this release; they receive the App v3 update via app stores. Hardware rollout follows standard supply chain fulfillment; no feature flag required for hardware.

## App (Software) Staged Rollout

| Stage | % of Users | Date | Gate Condition |
| --- | --- | --- | --- |
| Canary | 1% | Nov 10 | Zero Sev-1; p99 app launch < 3s |
| Stage 1 | 10% | Nov 14 | Crash-free >= 99.7%; CARE contact rate holds |
| Stage 2 | 50% | Nov 18 (GA) | NPS >= 45 in beta cohort; no Sev-2 open > 24h |
| Full Rollout | 100% | Dec 5 | All metrics stable for 7 days at 50% |

Feature flags are managed via AT&T's LaunchDarkly instance. Rollback is instant via flag toggle; no app-store submission required. Gateway firmware rollout is managed separately via the OTA orchestration platform with a matching percentage ramp.

# 11. Go / No-Go Criteria

| Criterion | Threshold (Go) | Owner | Measurement Method |
| --- | --- | --- | --- |
| Crash-free session rate | >= 99.5% | QA Lead | Firebase Crashlytics (7-day rolling) |
| App launch p99 latency | <= 3.0 sec | Eng / Perf | Datadog RUM synthetic monitor |
| Self-install completion rate | >= 88% | Product PM | Install flow funnel in Amplitude |
| Open Sev-1 bugs | Zero | QA Lead | Jira release board |
| Open Sev-2 bugs | <= 3, all with workaround | QA Lead | Jira release board |
| Legal / Regulatory sign-off | Written approval | Legal | Sign-off email on record |
| CARE readiness (agents trained) | >= 95% agent completion | CX Ops | LMS completion report |
| Supply chain inventory | >= 90 days of demand buffer | Supply Chain | SAP inventory report |

# 12. Launch Readiness Checklist

## Engineering

- All P0 and P1 bug fixes merged and tested

- Performance regression tests passed (p99 latency, throughput benchmarks)

- Security penetration test completed — no Critical/High findings open

- OTA rollback tested and verified on AirGateway 7 hardware

- App Store and Google Play submissions approved and staged

## QA

- Full regression suite passed on iOS 17+, Android 13+ device matrix

- Wi-Fi 7 MLO functionality verified on 6 GHz / 5 GHz / 2.4 GHz bands

- Signal IQ AR guidance validated in 8 RF environment scenarios

- Load test: 10,000 concurrent activations — no timeouts

## Documentation & Support

- In-box Quick Start Guide finalized and printed (6 languages)

- Help Center articles published: install, troubleshoot, upgrade

- CARE agent training completed: 95% of agents, 8-module curriculum

- IVR tree updated with Internet Air 2.0 flow

## Marketing & Communications

- Press release approved by Corporate Communications

- AT&T.com product pages updated with Wi-Fi 7 messaging

- In-store POS materials shipped to 4,200+ AT&T retail locations

- Email campaign to 2.3M existing subscribers — upgrade messaging

## Legal & Compliance

- FCC equipment authorization (FCC ID) obtained for AirGateway 7

- CPNI disclosure updated for auto-provisioning data usage

- Advertising claims reviewed — throughput claims legally defensible

# 13. Rollback Plan

## Triggers for Rollback

- Crash-free session rate drops below 98.5% for any 30-minute window

- Any Sev-1 defect confirmed post-GA that cannot be hot-fixed within 4 hours

- CARE contact rate exceeds 0.22 contacts/sub/day (20% above baseline)

- OTA firmware brick rate exceeds 0.01% of devices in any batch

## Rollback Steps

- Step 1: On-call engineer toggles LaunchDarkly flag — App v3 new-user traffic reverts to App v2 within 2 minutes

- Step 2: OTA orchestration platform pauses firmware rollout to AirGateway 7 devices not yet updated

- Step 3: Release manager pages VP Engineering and SVP Consumer Broadband within 15 minutes of trigger

- Step 4: Incident bridge opened; root cause SLA = 2 hours

- Step 5: Communications team notified — subscriber-facing message prepared within 1 hour if > 50K impacted

- Step 6: Postmortem scheduled within 48 hours; re-release gated on postmortem completion

# 14. Stakeholder Communication Plan

| Audience | Channel | Owner | Timing | Message |
| --- | --- | --- | --- | --- |
| C-Suite / Board | Exec briefing deck | SVP CB Products | Nov 13 (T-5) | Launch readiness, business case |
| CARE Center Agents | LMS training + email | CX Ops | Nov 3–14 | New product features, FAQs |
| Retail Store Staff | Field ops bulletin | Sales Enablement | Nov 10 | Sell sheet, demo script |
| Existing Subscribers | Email + push notif. | CRM / Marketing | Nov 18 (GA Day) | New app available, upgrade offer |
| Press / Media | Press release + briefing | Corp Comms | Nov 18 (GA Day) | Wi-Fi 7 leadership, performance stats |
| Internal Eng Teams | Slack #ia-launch + email | Release Manager | Nov 17 (T-1) | Go/no-go status, rollout plan |

# 15. Dependencies & Risks

| Dependency / Risk | Severity | Description | Mitigation |
| --- | --- | --- | --- |
| Nokia AX7200 supply chain | High | Gateway hardware depends on Nokia fab capacity in Taiwan; geo-political risk | 90-day buffer stock; secondary ODM qualified |
| Apple App Store review timeline | Medium | App Store review can take 5–10 days; must submit by Nov 7 | Early submission Nov 4; expedited review request filed |
| 5G C-band interference (winter) | Medium | Precipitation fade on C-band may reduce throughput in northern markets | Signal IQ thresholds calibrated for seasonal patterns |
| CARE surge on launch day | Low | App launch may drive 2x normal CARE volume for first 48 hours | Surge staffing +15% on Nov 18–20; IVR deflection flows ready |
| Regulatory (FCC ID) | Low | FCC ID authorization required before any commercial sale | FCC ID obtained Sep 2025; no blockers anticipated |