SoundCloud Creator Monetization

Product Roadmap & Release Plan

Fan-Powered Royalties 2.0 + Creator Analytics

| Classification: Confidential | Division: Creator Platform | Date: June 2025 | Version: 2.0 |
| --- | --- | --- | --- |

# 1. Executive Summary

SoundCloud pioneered Fan-Powered Royalties (FPR) in 2021, shifting from pro-rata streaming payouts to a user-centric payment model where each listener's subscription or ad revenue goes directly to the artists they actually listen to. FPR 1.0 has paid out over $120M to independent artists and drove a 22% increase in creator retention.

This roadmap covers the 12-month Creator Monetization Platform evolution and the full release plan for Fan-Powered Royalties 2.0 + Creator Analytics — GA targeted for Q3 2025. FPR 2.0 addresses the top creator feedback items: real-time payout dashboards, fan engagement signals, tiered fan subscriptions, and expanded eligibility to all SoundCloud Pro users.

# 2. Vision / North Star

"Make every serious creator on SoundCloud financially sustainable — so the next generation of music comes from here first."

# 3. Strategic Themes

## Theme 1 — Radical Payout Transparency

Creators today see a check but not the math. FPR 2.0 introduces a real-time royalty calculator that shows creators exactly how each stream, each fan subscription, and each ad impression translates into dollars. Every payout line item is traceable — from listener play to bank deposit.

## Theme 2 — Fan Monetization Beyond Streams

Expand revenue surfaces beyond passive streaming. FPR 2.0 introduces tiered Fan Subscriptions (Supporter, Super Fan, Devotee) where fans directly back creators at $2.99, $7.99, or $14.99/month. Additionally, Tips let fans one-time-pay creators after a particularly moving track. These direct revenues sit outside the royalty pool and go 100% to creators (minus payment processing).

## Theme 3 — Creator Analytics Intelligence

SoundCloud has rich behavioral data that creators cannot access today. Creator Analytics 2.0 surfaces: fan cohort retention curves, skip-vs-replay signals by track section, listener geography heat maps, playlist add velocity, and social share tracking. Weekly AI-generated insights ('Your Tuesday releases perform 34% better') help creators optimize without needing data science skills.

## Theme 4 — Monetization Eligibility Expansion

FPR 1.0 required 1,000 plays/month to qualify. FPR 2.0 drops the barrier to 500 plays/month and extends eligibility to all SoundCloud Pro Unlimited subscribers globally (from US/UK/DE/AU only). This expands the monetizing creator base from 140K to an estimated 380K.

# 4. Roadmap Timeline

| Initiative | Q2 2025 | Q3 2025 | Q4 2025 | Q1 2026 |
| --- | --- | --- | --- | --- |
| Fan-Powered Royalties 2.0 Core | Beta | GA |  |  |
| Creator Analytics Dashboard 2.0 | Alpha | GA |  |  |
| Fan Subscriptions (3-tier) | Dev | Beta | GA |  |
| Tips / One-time Payments |  | Beta | GA |  |
| AI Insights Engine |  |  | Beta | GA |
| Eligibility Expansion (500 plays) |  | GA |  |  |

# 5. Key Initiatives

## 5.1 Fan-Powered Royalties 2.0

- Real-time payout ledger: per-stream, per-fan-subscription, per-ad revenue — updated daily

- Payout minimum lowered from $10 to $5 threshold; weekly payout option (was monthly)

- Expanded territory eligibility: 85 countries (was 15)

- Eligible plays threshold: 500/month (was 1,000/month)

- Integration with Stripe Connect for instant payouts to creator bank accounts

## 5.2 Creator Analytics 2.0

- Track-level analytics: plays, unique listeners, reposts, comments, likes — 90-day trend

- Fan cohort analysis: new vs. returning listeners by week

- Section-level skip heatmap: visual waveform overlay showing where listeners drop off

- Playlist add velocity: track momentum from algorithmic and editorial playlists

- Export to CSV and Chartmogul-compatible API for advanced creators

# 6. Success Metrics

| Metric | Baseline (Q2 2025) | Target (Q4 2025) | Timeframe | Owner |
| --- | --- | --- | --- | --- |
| Monetizing creator count | 140K | 380K | Q4 2025 | Creator PM |
| Total creator payout (annualized) | $120M | $200M | Q4 2025 | Finance |
| Creator 90-day retention | 58% | 72% | Q4 2025 | Analytics |
| Fan subscription take rate | 0 (new) | 5% of creators | Q1 2026 | Monetization |
| Analytics DAU (creator) | 22% | 55% | Q4 2025 | Product |
| Avg payout per creator/month | $71 | $120 | Q1 2026 | Finance |

PART B — RELEASE PLAN

Fan-Powered Royalties 2.0 + Creator Analytics — GA

# 7. Release Overview

| Release Name | Fan-Powered Royalties 2.0 + Creator Analytics |
| --- | --- |
| Version | Creator Platform v6.0.0 / API v4.2 |
| Target GA Date | September 9, 2025 |
| Release Type | Major — new royalty model + analytics rebuild |
| Release Manager | Creator Monetization PM |
| Exec Sponsor | Chief Product Officer |

# 8. Release Scope

| IN SCOPE | OUT OF SCOPE (Deferred) |
| --- | --- |
| - FPR 2.0 royalty engine (daily real-time ledger) - Eligibility expansion: 500 plays/month, 85 countries - Creator Analytics Dashboard 2.0 - Section-level skip heatmap (waveform overlay) - Stripe Connect payout integration (weekly payouts) - Payout history CSV export | - Fan Subscriptions 3-tier (Q4 2025) - One-time Tips / direct payments (Q4 2025) - AI Insights engine (Q1 2026) - Label / distributor payout splitting - Mobile app analytics UI (web only at launch) |

# 9. Release Timeline

| Phase | Date | Owner | Exit Criteria |
| --- | --- | --- | --- |
| Feature Freeze | Jul 11, 2025 | Engineering | All royalty calculation logic merged; no open P0 |
| Dev Complete + QA Start | Jul 25, 2025 | Eng / QA | Payout reconciliation tests passing; analytics API stable |
| Internal Alpha (SoundCloud staff) | Aug 4 – Aug 15, 2025 | QA + Product | 300 employee accounts; payout math verified by Finance |
| Closed Beta (invited creators) | Aug 18 – Aug 29, 2025 | Creator PM | 2,000 creators; NPS >= 40; zero payout calculation errors |
| Canary Rollout (5% creators) | Sep 2 – Sep 5, 2025 | Eng / Ops | No payout discrepancies; API p99 < 800ms |
| GA (all eligible creators) | Sep 9, 2025 | Release Mgmt | 100% eligible creator base; Stripe payouts processing |

# 10. Rollout Strategy

## Creator Eligibility Rollout

FPR 2.0 eligibility is determined server-side. New eligibility rules activate via feature flag per creator account. The royalty engine migration runs in parallel (shadow mode) for 4 weeks before cutover — both FPR 1.0 and FPR 2.0 engines run simultaneously; creators switch to FPR 2.0 payouts only after Finance validates the parallel run outputs match expected distributions.

| Stage | % Creators | Date | Gate Condition |
| --- | --- | --- | --- |
| Shadow Mode | 100% (parallel) | Jul 14 – Aug 13 | FPR 2.0 calcs match Finance-validated expected amounts |
| Canary | 5% eligible | Sep 2 | Zero payout errors; creator support tickets < 0.5% |
| Stage 1 | 25% | Sep 5 | Stripe batch processing successful; no reconciliation errors |
| Stage 2 | 75% | Sep 8 | Analytics dashboard load time p99 < 2s at scale |
| Full GA | 100% | Sep 9 | All metrics stable; Finance sign-off on first payout cycle |

# 11. Go / No-Go Criteria

| Criterion | Threshold (Go) | Owner | Measurement |
| --- | --- | --- | --- |
| Payout calculation accuracy | 100% — zero rounding errors | Finance | Parallel run reconciliation report |
| Stripe payout processing | 100% of test payouts cleared | Finance / Stripe | Stripe Connect sandbox + production test run |
| Analytics API p99 latency | <= 800ms at 10K concurrent creators | Eng / Infra | Locust load test results |
| Open Sev-1 bugs | Zero | QA Lead | Linear issue tracker |
| Creator beta NPS | >= 40 | Creator PM | Typeform survey — closed beta cohort |
| Legal / Music licensing sign-off | Written approval from legal + label partners | Legal | Signed addendum from label partners |
| GDPR / financial data compliance | DPO sign-off (EU creator payouts) | Legal / DPO | Data protection impact assessment complete |

# 12. Launch Readiness Checklist

## Engineering & Finance

- Royalty engine shadow mode validated: FPR 2.0 vs FPR 1.0 delta within 0.001% for all test accounts

- Stripe Connect integration: production credentials active, webhook validation passing

- Analytics data pipeline backfill complete: 12 months of historical data available on day 1

- All API endpoints load-tested to 50K concurrent creators without degradation

- Rollback feature flag tested: reverts to FPR 1.0 calculations within 60 seconds

## QA

- Payout edge cases tested: zero plays month, DMCA-disputed tracks, collaborative uploads

- Multi-currency payout tested: USD, EUR, GBP, AUD — 8 additional currencies

- Analytics dashboard cross-browser: Chrome, Firefox, Safari, Edge — no regressions

- Screen reader accessibility audit completed for dashboard (WCAG 2.1 AA)

## Creator Communications

- Email campaign to 140K existing FPR creators: migration timeline and what changes

- Email campaign to 240K newly eligible Pro Unlimited creators: how to enroll

- Help center articles updated: 24 articles revised, 8 new articles published

- Creator FAQ webinar scheduled: Aug 28, 2025 — 2 sessions (US/EU time zones)

- YouTube tutorial video: 'Your New Creator Dashboard' — published Sep 9

## Legal & Compliance

- Music licensing addendum signed with major label distributors (Universal, Sony, WMG, Merlin)

- GDPR Data Protection Impact Assessment completed and approved by DPO

- Stripe merchant agreement updated for expanded territory payouts

# 13. Rollback Plan

## Rollback Triggers

- Any payout calculation discrepancy > 0.1% vs. Finance-validated expected amounts

- Stripe batch payout failure affecting > 100 creator accounts

- Analytics data serving incorrect metrics (verified by 3+ creator reports)

- Any regulatory hold from a market regulator on financial service operations

## Rollback Steps

- Step 1: Feature flag toggles FPR 2.0 off — affected creators revert to FPR 1.0 payouts within 5 minutes

- Step 2: Stripe batch paused — no payouts processed until root cause identified

- Step 3: Finance team notified immediately; payout reconciliation audit initiated

- Step 4: Creator-facing message posted to SoundCloud Creator Blog within 2 hours

- Step 5: If financial regulatory issue: Legal notified within 1 hour; market-specific action taken

- Step 6: Post-incident review within 5 business days; re-launch gated on Finance and Legal sign-off

# 14. Stakeholder Communication Plan

| Audience | Channel | Owner | Timing | Message |
| --- | --- | --- | --- | --- |
| Executive Team | Leadership deck | CPO | Sep 2 (T-7) | Business case, creator growth projections |
| Existing FPR Creators (140K) | Email + in-app | Creator PM | Aug 25 (T-15) | What changes, new payout timeline |
| Newly Eligible Creators (240K) | Email campaign | Growth / Marketing | Sep 9 (GA Day) | How to enroll, eligibility criteria |
| Label / Publisher Partners | Partner briefing call | Partnerships | Sep 3 (T-6) | Licensing addendum, payout model details |
| Press / Music Industry Media | Press release | Corp Comms | Sep 9 (GA Day) | Creator economy leadership position |
| Creator Support Team | Internal briefing + KB | Creator Success | Sep 2 (T-7) | New platform FAQs, escalation path |

# 15. Dependencies & Risks

| Dependency / Risk | Severity | Description | Mitigation |
| --- | --- | --- | --- |
| Label partner licensing addenda | High | Expanded territory payouts require updated licensing from major labels | Addenda in final review; 4-week legal negotiation buffer built in |
| Stripe Connect territory limits | High | Stripe Connect not available in all 85 target countries | Fallback: PayPal Payouts for unsupported countries; 12 affected |
| Data pipeline backfill volume | Medium | 12 months of historical analytics data: 8TB processing over 3 weeks | Snowflake cluster scaled up Aug 1; backfill started in parallel to dev |
| Creator confusion / support surge | Medium | Model change may cause payout confusion and support ticket spike | Detailed email comms, in-app explainer, creator FAQ webinar |
| Music rights disputes (DMCA) | Low | DMCA-disputed tracks must be excluded from payout calculations | Rights management API integration unchanged from FPR 1.0 |