Notion AI Workspace

Product Roadmap & Release Plan

AI Connectors: Slack, GitHub, Jira Integration

| Classification: Confidential | Division: Platform & AI | Date: June 2025 | Version: 1.0 |
| --- | --- | --- | --- |

# 1. Executive Summary

Notion AI has grown from a writing assistant to the connective tissue of knowledge work — used by 4 million paying teams to write, organize, plan, and now increasingly to answer questions across their entire organizational context. The single most requested capability since the AI launch is deep integration with the tools teams already live in: Slack, GitHub, and Jira.

This roadmap covers the 12-month Notion AI Platform evolution through Q2 2026, and the detailed release plan for Notion AI Connectors (Slack/GitHub/Jira) — GA targeted for October 2025. AI Connectors allow Notion AI to read, reference, and act on live data across a team's tool stack, enabling answers like 'Summarize all Jira tickets assigned to this project' or 'Draft a page from last week's Slack design review thread.'

# 2. Vision / North Star

"Be the AI layer that knows your company — your documents, your conversations, your code, your projects — so every team member can work with the full context of their organization, not just the file in front of them."

# 3. Strategic Themes

## Theme 1 — Connected Knowledge Graph

Notion's true competitive moat is being the system of record where institutional knowledge lives. AI Connectors extend this moat: Slack threads, GitHub PRs, and Jira epics become first-class Notion knowledge sources. The AI can answer cross-tool questions by traversing a unified knowledge graph, not just searching within Notion.

## Theme 2 — AI Agents with Contextual Grounding

Generic LLM responses fail when they lack company context. Notion AI Connectors provide retrieval-augmented generation (RAG) grounded in real organizational data — the specific Slack channel where the decision was made, the exact GitHub PR that broke the build, the specific Jira sprint that slipped. Grounded answers reduce hallucinations and increase trust.

## Theme 3 — Workflow Automation Across Tools

Beyond Q&A, AI Connectors enable cross-tool automation. Create a Notion page from a resolved GitHub issue. Auto-update a Jira ticket status when a Notion project status changes. Alert a Slack channel when a Notion doc is published. These workflows eliminate the copy-paste tax that consumes 30% of knowledge workers' days.

## Theme 4 — Enterprise Trust & Governance

Enterprise buyers won't connect sensitive data without control. Notion AI Connectors launches with workspace-level connector policies: admins control which connectors are enabled, which channels/repos/projects are included in AI context, and what data is retained in Notion's context cache. SOC 2 Type II and GDPR compliance certified at launch.

# 4. Roadmap Timeline

| Initiative | Q3 2025 | Q4 2025 | Q1 2026 | Q2 2026 |
| --- | --- | --- | --- | --- |
| AI Connectors: Slack | Beta | GA |  |  |
| AI Connectors: GitHub | Beta | GA |  |  |
| AI Connectors: Jira | Alpha | GA |  |  |
| Cross-tool Workflow Automation |  | Alpha | Beta | GA |
| AI Connectors: Google Workspace |  | Planning | Beta | GA |
| Connector Admin Policy Console | Dev | GA |  |  |

# 5. Key Initiatives

## 5.1 Slack Connector

- Read access to public channels and DMs where the Notion bot is invited

- AI can summarize threads, extract decisions, and generate Notion pages from conversations

- Temporal context: AI filters by date range — 'decisions from last sprint' works correctly

- Privacy: DMs only included with explicit workspace admin opt-in; user-level overrides

- Slack bot appears in Notion sidebar with channel selection UI

## 5.2 GitHub Connector

- Repository-level read access: PRs, issues, commits, code review comments

- AI can answer: 'What are the open issues in the auth service?' with real-time GitHub data

- Commit-to-doc linking: GitHub PR descriptions can auto-populate linked Notion changelog entries

- Code snippet embedding in Notion pages with live GitHub sync

## 5.3 Jira Connector

- Project and issue read access: epics, stories, bugs, sprint boards

- AI status queries: 'How many P0 bugs are open in Q3?' answered from live Jira data

- Sprint summary generation: auto-create Notion sprint review pages from Jira sprint data

- Bidirectional status sync: Notion project status updates reflected in linked Jira epic status

# 6. Success Metrics

| Metric | Baseline | Target | Timeframe | Owner |
| --- | --- | --- | --- | --- |
| Connector activations (workspaces) | 0 (new) | 15K workspaces | Q1 2026 | Platform PM |
| AI query grounding rate | 12% (Notion-only) | 40% (cross-tool) | Q1 2026 | AI Eng |
| Notion AI MAU retention (w/ connectors) | 61% | 78% | Q1 2026 | Analytics |
| Enterprise plan attachment rate | 22% | 35% | Q2 2026 | Sales |
| Cross-tool query satisfaction (CSAT) | N/A | >= 4.2 / 5 | Q1 2026 | Product |
| Connector-related churn prevention | N/A | < 0.8% monthly churn for connector users | Q2 2026 | Growth |

PART B — RELEASE PLAN

Notion AI Connectors (Slack / GitHub / Jira) — GA

# 7. Release Overview

| Release Name | Notion AI Connectors: Slack, GitHub, Jira — General Availability |
| --- | --- |
| Version | Notion Platform v2.12 / Connector API v1.0 |
| Target GA Date | October 14, 2025 |
| Release Type | Major — new platform capability (connectors framework) |
| Release Manager | Platform PM — AI & Integrations |
| Exec Sponsor | Head of Product |

# 8. Release Scope

| IN SCOPE — October 14 GA | OUT OF SCOPE (Future Releases) |
| --- | --- |
| - Slack connector: channel summary + Notion page creation - GitHub connector: issues, PRs, commit search - Jira connector: project/sprint read + sprint summary gen - Connector Admin Policy Console (Enterprise plan) - User-level privacy controls per connector - SOC 2 Type II and GDPR compliance for connector data | - Google Workspace connector (Q2 2026) - Cross-tool workflow automation (Q2 2026) - Salesforce / HubSpot connectors - Notion-to-Jira write-back (bidirectional Jira) - Third-party connector SDK (developer ecosystem) |

# 9. Release Timeline

| Phase | Date | Owner | Exit Criteria |
| --- | --- | --- | --- |
| Feature Freeze | Aug 8, 2025 | Platform Eng | Connector API v1.0 stable; all 3 connectors functionally complete |
| Dev Complete + Security Audit | Aug 22, 2025 | Eng / Security | Penetration test passed; no Critical/High findings open |
| Internal Alpha (Notion employees) | Aug 25 – Sep 5, 2025 | QA + Product | 400 employees; Slack/GitHub/Jira connectors tested in prod workspaces |
| Closed Beta (enterprise customers) | Sep 8 – Sep 26, 2025 | CSM + Product | 50 enterprise workspaces; CSAT >= 4.0; no Sev-1 open |
| Open Beta (Plus/Business plan) | Sep 29 – Oct 10, 2025 | Product + Eng | 2,000 workspaces; connector error rate < 1% |
| GA — All plans (staged) | Oct 14, 2025 | Release Mgmt | Phased rollout 10% -> 50% -> 100%; all metrics green |

# 10. Rollout Strategy

AI Connectors are gated by a workspace-level feature flag managed in LaunchDarkly. Rollout targets workspaces by plan tier (Enterprise first, then Business, then Plus, then free). Within each tier, workspaces are randomly sampled. All connector data retrieval is server-side; no client app update required for the rollout.

| Stage | % Workspaces | Date | Gate Condition |
| --- | --- | --- | --- |
| Enterprise Early Access | 5% Enterprise | Oct 14 | Closed beta success; SOC 2 audit report available |
| Stage 1 | 25% Enterprise + 10% Business | Oct 16 | Connector error rate < 0.5%; p99 latency < 4s |
| Stage 2 | 100% Enterprise + 50% Business | Oct 20 | No Sev-1; support ticket rate < 2% of activated workspaces |
| Full GA | All plan tiers | Oct 28 | All metrics stable for 7 days at Stage 2 scale |

# 11. Go / No-Go Criteria

| Criterion | Threshold (Go) | Owner | Measurement |
| --- | --- | --- | --- |
| Connector error rate | < 1% of connector requests | Eng / Infra | Datadog connector error dashboard (24h rolling) |
| AI response grounding accuracy | >= 85% factually correct vs. source | AI Eng | Human eval on 200-sample golden dataset |
| Connector auth latency p99 | <= 4.0 seconds per query | Eng | Datadog APM trace p99 |
| Security pentest | Zero Critical or High findings open | Security Eng | Pentest report from external firm |
| SOC 2 Type II attestation | Report issued (connectors in scope) | Security / Legal | Auditor attestation letter |
| Open Sev-1 bugs | Zero | QA Lead | Linear milestone at release |
| GDPR Data Processing Agreements | DPA updated for EU enterprise customers | Legal | Legal review completion memo |

# 12. Launch Readiness Checklist

## Engineering & Security

- Connector API v1.0 documentation published at developers.notion.com

- External penetration test completed — no Critical/High findings open

- SOC 2 Type II audit scope updated to include connector data flows

- Rate limiting and abuse detection active for all connector API endpoints

- Data retention: connector context cache TTL = 24 hours; no long-term storage of third-party data

## QA & Performance

- Functional testing across Slack, GitHub, Jira sandbox environments — all test cases green

- Load testing: 10,000 concurrent connector queries — p99 < 4s, error rate < 0.1%

- Connector activation flow tested on all supported browsers and Notion desktop app

- Connector disable / data purge flow verified — all third-party tokens revoked within 60s

## Documentation & Support

- Notion Help Center: 12 new articles covering connector setup, troubleshooting, admin controls

- Enterprise admin guide: Connector Policy Console documentation

- Support team trained on connector-specific troubleshooting flows

- In-app onboarding flow: connector setup wizard with animated guidance

## Legal & Compliance

- Slack, GitHub, Jira API Terms of Service compliance review completed

- GDPR Data Processing Agreements updated for connector data processing

- Privacy policy updated to disclose connector data handling

## Go-to-Market

- Press release approved: 'Notion AI now works across your entire tool stack'

- Product Hunt launch prepared for Oct 14

- Enterprise sales enablement deck updated with connector ROI story

- 10 customer success stories secured from closed beta participants

# 13. Rollback Plan

## Rollback Triggers

- Connector error rate exceeds 5% for any 15-minute window post-GA

- Any confirmed data leakage between workspaces via connector context

- Third-party credential exposure (Slack/GitHub/Jira OAuth tokens)

- Sev-1 defect confirmed post-GA without hot-fix available within 2 hours

## Rollback Steps

- Step 1: LaunchDarkly flag toggled — connectors disabled globally within 2 minutes

- Step 2: All active OAuth sessions revoked via each platform's revocation API

- Step 3: Connector context cache purged from Notion servers

- Step 4: Engineering on-call pages Head of Engineering and Head of Product within 15 minutes

- Step 5: If data leakage: Legal + Security notified; GDPR breach assessment initiated

- Step 6: Status page (status.notion.so) updated within 30 minutes of confirmed incident

- Step 7: Enterprise CSMs notified to brief affected customers within 1 hour

# 14. Stakeholder Communication Plan

| Audience | Channel | Owner | Timing | Message |
| --- | --- | --- | --- | --- |
| Enterprise Customers | CSM briefing + email | Customer Success | Oct 7 (T-7) | Early access, admin policy controls |
| All Notion Users | In-app banner + email | Product Mktg | Oct 14 (GA Day) | Connector setup CTA, use case examples |
| Press / Tech Media | Embargoed press kit | Corp Comms | Oct 13 (T-1) | Platform vision, enterprise differentiation |
| Developer / ISV Community | Developer changelog | DevRel | Oct 14 (GA Day) | Connector API v1.0 docs, connector SDK timeline |
| Sales Team | Internal Slack + deck | Product Mktg | Oct 10 (T-4) | Competitive positioning vs. Confluence AI |
| Board / Investors | Board update memo | CEO / CPO | Oct 15 (T+1) | Connector activation metrics, ARR impact |

# 15. Dependencies & Risks

| Dependency / Risk | Severity | Description | Mitigation |
| --- | --- | --- | --- |
| Slack API policy changes | High | Slack has restricted third-party AI integrations in the past; policy may change | Direct partnership with Salesforce (Slack parent); preferential API access agreement |
| GitHub Copilot competitive response | High | GitHub may restrict Notion's API access as Copilot expands to competitive use cases | API agreement in place; Terms of Service reviewed by Legal |
| RAG latency at scale | Medium | Retrieval + generation adds 2-4s to AI query response at 10K concurrent users | Vector cache, connector-specific embedding pre-computation, streaming responses |
| OAuth token security | Medium | Storing third-party OAuth tokens creates new attack surface | Tokens encrypted at rest (AES-256); stored in HSM-backed secret manager |
| Atlassian (Jira) API rate limits | Low | Jira Cloud API rate limit: 500 req/10 min per integration | Request queuing, per-workspace rate limit management, Atlassian partnership tier |