THE WALT DISNEY COMPANY

Disney+ Ad-Supported Tier Launch & Scaling

Business Case & Product Proposal

| Classification: | CONFIDENTIAL — Executive Review Only |
| --- | --- |
| Prepared For: | Executive Review Board, The Walt Disney Company |
| Prepared By: | Disney+ Direct-to-Consumer Strategy Office |
| Date: | Q2 2025 |
| Version: | 2.0 — Final for Board Review |

# 1. Executive Summary

The Ask: Disney+ requests Board approval for a $1.22B Year 1 investment to fully launch and scale the Disney+ ad-supported tier ("Disney+ Basic") to 65 million ad-tier subscribers globally by end of FY2027, supported by a proprietary ad technology platform, addressable advertising infrastructure, and a $450M marketing campaign.

The Opportunity: Streaming profitability is the defining challenge for Disney's DTC segment. Netflix's ad-supported tier attracted 40M subscribers in 18 months, validating dual-tier monetization at scale. Disney+ commands one of the world's most valuable content libraries (Marvel, Star Wars, Pixar, Disney Animation, National Geographic), yet over 35% of price-sensitive potential subscribers cite cost as the primary barrier to sign-up. The ad-supported tier at $7.99/month unlocks this segment while generating an additional $6.00/month per subscriber in advertising revenue, delivering superior ARPU to the $13.99 premium tier after ad costs.

The Recommendation: Approve the Disney+ Ad Tier Scale Program at $3.82B total 3-year investment, targeting a 3-year NPV of $6.6B (10% discount rate), payback in Q1 Year 1, and a cumulative ROI of 320% by Year 3.

# 2. Problem / Opportunity Statement

Disney+ faces a structural monetization gap: the service must grow subscribers while moving toward profitability. Three forces converge to make the ad tier expansion the right move now:

- Profitability Mandate: Disney DTC lost $11.4B cumulatively through FY2023. The ad tier generates ~$14/month effective ARPU ($7.99 sub fee + $6 ad rev) vs. $13.99 for premium — with significantly higher subscriber volume potential.

- Market Validation: Netflix ad tier reached 40M MAUs in 18 months with CPMs 3x premium streaming averages. Peacock and Max ad tiers generate 60-70% of their subscriber growth from the ad-supported option. The market has spoken.

- First-Party Data Moat: Disney's 157M global subscriber base, combined with parks, merchandise, and ESPN data, creates a first-party data asset that commands premium CPMs ($50-85 CPM vs. industry avg $15) from advertisers seeking brand-safe family content adjacency.

# 3. Proposed Solution (Product Proposal)

We propose the Disney+ Ad Tier Scale Program — three integrated product workstreams:

## Workstream 1: Proprietary Ad Technology Platform (Q3 2025)

- Build Disney Advertising Technology stack (DAT): server-side ad insertion, dynamic ad pod optimization, frequency capping, and brand safety controls. Reduces dependency on third-party SSPs from 80% to 30%, capturing $2-3 CPM margin improvement.

- Integrate Disney Clean Room: privacy-preserving audience matching across Disney's ecosystem (streaming + parks + ESPN) enabling cross-platform targeting without third-party cookies.

## Workstream 2: Ad Product Expansion (Q4 2025)

- Launch Pause Ads, QR-activated shoppable ads, and branded content integrations within Disney original productions. These premium ad formats command 60-120% CPM premiums over standard pre-roll.

- Programmatic Guaranteed (PG) inventory for Fortune 500 advertisers: minimum $10M annual commitments in exchange for premium placement and audience guarantees.

## Workstream 3: Subscriber Acquisition & Tier Migration (Q3 2025 - Q4 2027)

- Targeted acquisition campaigns in price-sensitive segments (Gen Z, families with children, emerging markets). Reduce effective cost of acquisition by 40% vs. premium tier CAC via lower price point.

- Intelligent tier migration: nudge premium churners to ad tier before cancel (estimated 18-22% save rate based on Netflix benchmarks).

# 4. Strategic Alignment

| Disney Strategic Priority | Ad Tier Contribution | Target Metric |
| --- | --- | --- |
| DTC Profitability by FY2026 | Ad tier doubles effective ARPU of price-sensitive segment; contributes $6.4B incremental revenue by Y3 | DTC segment profitability by Q2 FY2026 |
| Grow Total Disney+ Subscribers to 215M+ | Ad tier unlocks 35% of non-subscribers blocked by price; projects 65M ad-tier subs by Y3 | 215M total Disney+ subscribers by FY2027 |
| First-Party Data Leadership | Ad platform creates Disney Clean Room: industry-leading cross-screen targeting data asset | $85 average CPM for brand-safe inventory by Y2 |

# 5. Market Opportunity

| Metric | Definition | Size | Rationale |
| --- | --- | --- | --- |
| TAM | Global addressable streaming advertising market across all platforms | $84.0B annually by 2027 | eMarketer 2024 CTV ad spend forecast; growing at 18% CAGR driven by cord-cutting acceleration |
| SAM | Premium streaming ad market reachable by Disney+ (English-language + select international) | $22.0B annually | Disney addressable markets: US, UK, Canada, Australia, select EU; family/brand-safe premium CPM segment |
| SOM | Disney+ achievable ad revenue at 65M ad-tier subscribers at $6 ARPU/month | $4.68B annually (Y3) | Based on 65M subs x $6/mo ad revenue x 12 months; $6/mo = 300 ad mins/month x $0.20 avg CPM-equivalent |

# 6. Cost Breakdown ($M)

| Cost Category | Year 1 ($M) | Year 2 ($M) | Year 3 ($M) | 3-Year Total ($M) |
| --- | --- | --- | --- | --- |
| Engineering & Product (Ad Tech Platform Build) | $280 | $320 | $350 | $950 |
| Infrastructure / Cloud & Ad Delivery CDN | $180 | $220 | $260 | $660 |
| Marketing & GTM (Ad Tier Acquisition Campaign) | $450 | $380 | $310 | $1,140 |
| Operations (Ad Sales, Brand Safety, Policy) | $200 | $240 | $280 | $720 |
| Contingency (10% of direct costs) | $111 | $116 | $120 | $347 |
| TOTAL INVESTMENT | $1,221 | $1,276 | $1,320 | $3,817 |

# 7. Revenue Projections ($M)

| Revenue Driver | Year 1 ($M) | Year 2 ($M) | Year 3 ($M) | 3-Year Total ($M) |
| --- | --- | --- | --- | --- |
| Ad-Tier Subscription Fees (Subs x $7.99/mo x 12) | $2,397 | $4,315 | $6,232 | $12,944 |
| Advertising Revenue (Subs x $6.00/mo x 12) | $1,800 | $3,240 | $4,680 | $9,720 |
| Ad-Tier Subscribers (millions) | 25.0M | 45.0M | 65.0M | — |
| Effective ARPU (Sub fee + Ad rev) | $13.99/mo | $13.99/mo | $13.99/mo | $13.99/mo |
| TOTAL REVENUE | $4,197 | $7,555 | $10,912 | $22,664 |

# 8. 3-Year Financial Summary (P&L, $M)

| Line Item | Year 1 ($M) | Year 2 ($M) | Year 3 ($M) |
| --- | --- | --- | --- |
| Revenue | $4,197 | $7,555 | $10,912 |
| COGS (Content Delivery + Ad Tech + Payment Processing) | ($1,229) | ($2,212) | ($3,195) |
| Gross Margin | $2,968 | $5,343 | $7,717 |
| Gross Margin % | 70.7% | 70.7% | 70.7% |
| Operating Expenses (OpEx) | ($1,221) | ($1,276) | ($1,320) |
| EBITDA | $1,747 | $4,067 | $6,397 |
| EBITDA Margin % | 41.6% | 53.8% | 58.6% |

# 9. ROI Analysis

Discount Rate: 10% | All figures in $M

| Metric | Year 1 | Year 2 | Year 3 |
| --- | --- | --- | --- |
| Cumulative Investment ($M) | $1,221 | $2,497 | $3,817 |
| Cumulative EBITDA ($M) | $1,747 | $5,814 | $12,211 |
| Net Benefit (Cum. EBITDA - Cum. Investment) | $526 | $3,317 | $8,394 |
| ROI % (Net Benefit / Cumulative Investment) | 43.1% | 132.8% | 219.9% |
| Payback Period | Q1 Year 1 (EBITDA exceeds investment in Year 1) |
| NPV (3-Year, 10% Discount Rate) | $6,599M |
| IRR | >100% (Year 1 EBITDA alone exceeds Year 1 investment) |

NPV = PV(EBITDA streams) - PV(Investments) = ($1,747/1.10 + $4,067/1.21 + $6,397/1.331) - ($1,221/1.10 + $1,276/1.21 + $1,320/1.331) = $9,755M - $3,156M = $6,599M

# 10. Alternatives Considered

| Option | Description | Pros | Cons | Decision |
| --- | --- | --- | --- | --- |
| Do Nothing | Maintain premium-only Disney+ at $13.99/mo | No new investment; clean user experience | Misses $4.68B ad rev opportunity; slower subscriber growth; continued losses | Rejected: leaves $6.6B NPV on the table |
| Third-Party Ad Platform (Outsource) | License Magnite or FreeWheel for ad serving; no internal tech build | Faster time-to-market; lower upfront capex | $2-4 CPM margin loss to SSP fees; no data ownership; limited custom ad product capability | Rejected: margin and data ownership concerns outweigh speed benefit |
| Ad-Lite (10 min/hr ad load) | Launch with minimal ad load; lower CPM commitments | Better user experience; low churn risk | Projected 35% lower ad revenue vs. industry-standard 4 min/hr load; insufficient ROI | Rejected: insufficient to meet DTC profitability targets |
| Full Proposal (RECOMMENDED) | Proprietary ad tech + premium ad products + full subscriber scale-up | Maximum revenue; data ownership; competitive parity with Netflix | Highest investment; technology build risk | SELECTED: superior NPV and strategic value |

# 11. Risk Assessment

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Ad tech build delayed > 9 months | Medium | High | Bridge with FreeWheel SSP during build phase; gated go/no-go reviews at 90-day intervals; dedicated 80-person ad tech team |
| Premium subscriber cannibalization exceeds 15% | Medium | Medium | Differentiated content windows for premium tier; tiered content strategy tested via A/B analysis; Netflix data shows <12% premium tier migration |
| Advertiser CPM below $50 forecast | Low | High | Pre-launch commitments secured with 15 Fortune 500 advertisers at $55+ CPM; Programmatic Guaranteed contracts provide floor pricing |
| EU/Privacy regulation limits ad targeting | Medium | Low | Disney Clean Room designed for contextual targeting fallback; GDPR/DMA-compliant architecture from day one; EU ad revenue modeled conservatively at 60% of US CPM |
| Subscriber growth below 25M in Year 1 | Low | Medium | Bear case modeled at 18M Y1 subs: still EBITDA-positive at $1.2B Y1. Floor supported by Disney+ bundling with Hulu + ESPN+ |

# 12. Implementation Timeline

| Phase | Dates | Key Deliverables | Milestone |
| --- | --- | --- | --- |
| Phase 0: Architecture | Q2 2025 (Apr-Jun) | Finalize ad tech platform architecture; hire 80 ad tech engineers; execute 15 advertiser pre-launch commitments | Board approval; pre-launch ad commitments |
| Phase 1: Ad Tech Build | Q3 2025 (Jul-Sep) | SSAI (server-side ad insertion) live; brand safety controls; Disney Clean Room beta; first ad impressions served | Ad tech MVP live; 10M ad-tier subs |
| Phase 2: Premium Ad Products | Q4 2025 (Oct-Dec) | Pause Ads, shoppable QR ads, PG inventory live; holiday advertising sold out at $70+ CPM | 25M ad-tier subs; $1.8B ad run rate |
| Phase 3: International Scale | Q1-Q2 2026 (Jan-Jun) | Ad tier live in UK, Canada, Australia, Germany, France; localized ad sales teams hired; contextual targeting for EU | 38M ad-tier subs globally |
| Phase 4: Full Scale | Q3-Q4 2026 (Jul-Dec) | Full PG marketplace launch; live sports advertising integration via ESPN+; attribution reporting dashboard for advertisers | 45M ad-tier subs; $3.24B ad run rate |
| Phase 5: Optimize & Expand | Q1-Q4 2027 (Jan-Dec) | AI-driven ad pod optimization; dynamic creative optimization; shoppable commerce integrations; affiliate measurement | 65M ad-tier subs by Dec 2027 |

# 13. Recommendation & Ask

The Disney+ DTC Strategy Office recommends that the Executive Review Board approve the following program:

| Ask | Details |
| --- | --- |
| Capital Investment | $1,221M Year 1 / $1,276M Year 2 / $1,320M Year 3 = $3,817M total program budget |
| Headcount Authorization | 420 net new FTEs: 180 engineering (ad tech), 80 product & design, 100 ad sales, 60 operations & brand safety |
| Decision Requested | Board approval of full 3-year program with Q3 2025 ad tech MVP launch; quarterly Board updates on CPM and subscriber KPIs |
| Expected Outcome | 65M ad-tier subscribers by FY2027; $10.9B total revenue in Year 3; 3-year NPV $6.6B; IRR >100%; DTC profitability achieved Q2 FY2026 |

The Disney+ Ad-Supported Tier is the single highest-NPV initiative available to the DTC business unit in the next three years. With $6.6B in NPV, immediate payback in Year 1, and a IRR that exceeds the company's hurdle rate by a factor of 10x, this program represents an unambiguous investment imperative. We request full Board approval.