DOORDASH, INC.

DoorDash Grocery Vertical Expansion

Business Case & Product Proposal

| Classification: | CONFIDENTIAL — Executive Review Only |
| --- | --- |
| Prepared For: | Executive Review Board, DoorDash, Inc. |
| Prepared By: | New Verticals Strategy & Product Office |
| Date: | Q2 2025 |
| Version: | 1.0 — Final for Board Review |

# 1. Executive Summary

The Ask: DoorDash requests approval for a $671M Year 1 investment to fully commercialize the DoorDash Grocery vertical — scaling from $1.8B current grocery GMV to $12.5B grocery GMV by end of FY2027 through dedicated grocery Dashers, a national retail grocery partnership program (Kroger, Albertsons, Publix, HEB), and a proprietary dark-store micro-fulfillment network in the top 40 U.S. metros.

The Opportunity: Grocery delivery is a $260B annual opportunity in the U.S., currently captured primarily by Instacart ($29B GMV, 2024) while DoorDash has only 6.9% grocery delivery market share despite commanding 67% of U.S. restaurant delivery. DoorDash's infrastructure — 7M active Dashers, same-day logistics in 7,000 cities, and 37M DashPass members — is directly applicable to grocery with marginal incremental investment. Grocery orders carry a $62 average order value vs. $31 for restaurant, making each grocery conversion 2x more valuable per delivery.

The Recommendation: Approve the DoorDash Grocery Vertical Expansion at $2.16B total 3-year investment, targeting $12.5B grocery GMV in Year 3, $2.46B in annual platform revenue, and a 3-year NPV of $968M (10% discount rate) on the EBITDA stream, with payback in Q2 Year 2.

# 2. Problem / Opportunity Statement

DoorDash faces a structural gap between its delivery infrastructure dominance and its grocery market share. Four specific gaps must be addressed:

- Market Share Gap: Instacart holds 72% of U.S. grocery delivery market share. DoorDash holds 6.9%. DoorDash's restaurant delivery footprint in the same ZIP codes gives it a cost-shared fulfillment advantage that Instacart cannot match — but DoorDash is not yet exploiting it.

- Unit Economics Gap: Grocery on DoorDash today generates $4.20 contribution per order vs. $3.80 for restaurant due to higher AOV, but grocery-specific Dasher routing, picker efficiency, and cold-chain handling are not optimized. A dedicated grocery Dasher pool and in-store picker partnerships reduce per-order cost by an estimated $1.80, improving grocery contribution to $6.00/order.

- Retailer Partnership Gap: Kroger, Albertsons, and Publix currently split grocery delivery between Instacart (primary) and DoorDash (secondary). DoorDash has not offered a dedicated grocery partnership tier with inventory integration, in-store picker APIs, or preferred retailer pricing. This program does.

- Customer Frequency Gap: Restaurant customers order 4.2x/month; grocery customers order 2.1x/month. Converting existing DashPass members to grocery adds 2.1 incremental grocery orders/month per converting member, increasing DashPass LTV by $180/year.

# 3. Proposed Solution (Product Proposal)

We propose the DoorDash Grocery Vertical Scale Program — four integrated product and operational workstreams:

## Workstream 1: National Grocery Retailer Partnership Program (Q3 2025)

- Dedicated DoorDash Grocery Partner tier for top 20 grocery chains: real-time inventory API integration, in-store picker app for retailer employees, preferred slot access for DoorDash Dashers, and co-marketing campaign ($50M annual pool).

- Launch partners: Kroger (2,800 stores), Albertsons (2,200 stores), Publix (1,300 stores), HEB (380 stores). Combined $148B annual grocery revenue accessible via DoorDash.

## Workstream 2: Dedicated Grocery Dasher Pool (Q3 2025)

- Grocery-certified Dasher program: training on fresh produce handling, cold-chain packaging, and substitution protocols. Grocery-certified Dashers receive $2/order bonus, priority dispatch for grocery orders, and cold-storage equipment stipend ($120/Dasher).

- Target 400,000 grocery-certified Dashers by end of Year 1. Reduces substitution complaints by 58% and improves grocery order rating from 4.2 to 4.7 stars.

## Workstream 3: Dark Store Micro-Fulfillment Network (Q4 2025)

- Build 85 DoorDash-operated dark stores (2,500-5,000 sq ft) in the top 40 U.S. metros. Stocked with the top 2,500 SKUs by demand frequency. Sub-20-minute delivery on high-velocity items; expands DashMart to full grocery assortment.

## Workstream 4: Grocery-Optimized DashPass & AI Recommendations (Q1 2026)

- DashPass Grocery tier ($3/month grocery add-on or included in DashPass+): free delivery on all grocery orders, 5% grocery cashback, weekly personalized grocery list via AI recommendation engine.

# 4. Strategic Alignment

| DoorDash Strategic Priority | Grocery Expansion Contribution | Target Metric |
| --- | --- | --- |
| Grow Total Platform GMV to $100B+ by FY2027 | Grocery adds $12.5B incremental GMV (currently $1.8B); grocery is the largest category whitespace | $12.5B grocery GMV by FY2027 |
| Achieve Sustained Profitability (Adj. EBITDA+) | Grocery $6.00 contribution margin vs. $3.80 restaurant; scale effects reduce overhead per order; Y2 EBITDA positive | EBITDA positive Q2 Year 2 |
| Increase DashPass Member Frequency & LTV | Grocery converts DashPass from 4.2 restaurant orders to 6.3 total orders/month; $180/yr LTV increase per converting member | +2.1 grocery orders/mo for 37M DashPass members |

# 5. Market Opportunity

| Metric | Definition | Size | Rationale |
| --- | --- | --- | --- |
| TAM | Total U.S. grocery market (all channels: physical, online, delivery) | $1.2T annually | USDA / FMI 2024; U.S. grocery spend including supermarkets, club stores, specialty. Online grocery growing 18% annually. |
| SAM | U.S. online grocery delivery market (same-day and next-day delivery across all platforms) | $175B annually by 2027 | 14.6% of total grocery shifting online by 2027 (McKinsey 2024); Instacart + Walmart+ + Amazon Fresh are the incumbents |
| SOM | DoorDash addressable grocery GMV at 7.1% market share target by Year 3 | $12.5B GMV ($2.46B platform revenue) | Growth from 6.9% to 7.1% market share via retailer partnerships + dark stores; revenue = 12% commission + delivery fees + DashPass attribution |

# 6. Cost Breakdown ($M)

| Cost Category | Year 1 ($M) | Year 2 ($M) | Year 3 ($M) | 3-Year Total ($M) |
| --- | --- | --- | --- | --- |
| Engineering & Product (Inventory APIs, Grocery App, AI Recs) | $120 | $155 | $175 | $450 |
| Infrastructure (85 Dark Stores, Cold Chain Capex) | $65 | $90 | $115 | $270 |
| Marketing & GTM (Co-Marketing, DashPass Grocery) | $280 | $230 | $185 | $695 |
| Operations (Grocery Dasher Training, Picker Apps, Ops) | $145 | $185 | $220 | $550 |
| Contingency (10% of direct costs) | $61 | $66 | $70 | $197 |
| TOTAL INVESTMENT | $671 | $726 | $765 | $2,162 |

# 7. Revenue Projections ($M)

| Revenue Driver | Year 1 ($M) | Year 2 ($M) | Year 3 ($M) | 3-Year Total ($M) |
| --- | --- | --- | --- | --- |
| Retailer Commission Revenue (12% of Grocery GMV) | $504 | $936 | $1,500 | $2,940 |
| Net Delivery Fees (avg $1.50/order net of Dasher pay) | $225 | $390 | $600 | $1,215 |
| DashPass Grocery Attribution ($2/mo per grocery member) | $120 | $210 | $360 | $690 |
| Grocery GMV ($B) | $4.2B | $7.8B | $12.5B | — |
| TOTAL REVENUE | $849 | $1,536 | $2,460 | $4,845 |

# 8. 3-Year Financial Summary (P&L, $M)

| Line Item | Year 1 ($M) | Year 2 ($M) | Year 3 ($M) |
| --- | --- | --- | --- |
| Revenue | $849 | $1,536 | $2,460 |
| COGS (Dasher Pay, Picker Wages, Cold Chain) | ($254) | ($452) | ($708) |
| Gross Margin | $595 | $1,084 | $1,752 |
| Gross Margin % | 70.1% | 70.6% | 71.2% |
| Operating Expenses (OpEx) | ($671) | ($726) | ($765) |
| EBITDA | ($76) | $358 | $987 |
| EBITDA Margin % | (9.0%) | 23.3% | 40.1% |

# 9. ROI Analysis

Discount Rate: 10% | All figures in $M

| Metric | Year 1 | Year 2 | Year 3 |
| --- | --- | --- | --- |
| Cumulative Investment ($M) | $671 | $1,397 | $2,162 |
| Cumulative EBITDA ($M) | ($76) | $282 | $1,269 |
| Net Benefit (Cum. EBITDA - Cum. Investment) | ($747) | ($1,115) | ($893) |
| ROI % (Cumulative EBITDA / Cumulative Investment) | (11.3%) | 20.2% | 58.7% |
| Payback Period | Q2 Year 2 (EBITDA turns positive; cumulative payback by Q1 Year 4) |
| NPV (3-Year EBITDA Stream, 10% Discount Rate) | $968M |
| IRR | 44% (based on 5-year forward EBITDA projection) |

NPV = PV(EBITDA stream) = ($76)/1.10 + $358/1.21 + $987/1.331 = ($69.1) + $295.9 + $741.5 = $968.3M. Note: full investment payback (cumulative EBITDA exceeds cumulative investment) occurs Q1 Year 4 on current trajectory; Year 3 grocery vertical is EBITDA-profitable at $987M.

# 10. Alternatives Considered

| Option | Description | Pros | Cons | Decision |
| --- | --- | --- | --- | --- |
| Do Nothing | Maintain grocery as an organic add-on to restaurant delivery with no dedicated investment | No new capex; focus on core restaurant business | Instacart consolidates grocery market share; DoorDash misses $12.5B GMV opportunity; DashPass LTV stagnates | Rejected: leaves $968M NPV on table |
| Acquire Instacart or Shipt | Acquire an existing grocery delivery platform for $8-15B | Instant market share; established retailer relationships; proven tech | $8-15B acquisition premium; integration risk 18-24 months; Instacart IPO valuation out of range; antitrust risk | Rejected: build yields better capital efficiency and avoids antitrust exposure |
| Retailer Partnerships Only (No Dark Stores) | Sign retailer partnerships but skip dark store build; rely solely on store-pick model | $250M lower capex; faster to launch | Cannot offer sub-20-minute delivery on high-velocity SKUs; loses quick-commerce premium segment to Gopuff and DashMart | Rejected: dark stores are critical for sub-20-min delivery which commands 40% higher AOV |
| Full Proposal (RECOMMENDED) | Retailer partnerships + dedicated Dasher pool + dark stores + DashPass Grocery tier | Maximum GMV growth; full category coverage; highest DashPass LTV impact | Highest investment; 3-year program horizon | SELECTED: captures full $12.5B GMV opportunity |

# 11. Risk Assessment

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Kroger/Albertsons renew Instacart exclusivity | Medium | High | DoorDash preferred partner agreements offer 5% better commission rev-share than Instacart's current rates; dark store model is independent of retailer exclusivity; HEB and Publix already in advanced negotiations |
| Dark store unit economics underperform (AOV < $45) | Medium | Medium | Dark store model gated: open only if pilot 10-store cohort hits $52+ AOV and 18+ orders/day in first 90 days; current DashMart pilot at $58 AOV with 24 orders/day |
| Grocery Dasher certification adoption below 400K | Low | Medium | $2/order bonus drives high adoption; current opt-in pilot shows 73% of active Dashers interested; certification takes 2 hours and is fully mobile |
| Instacart launches restaurant delivery (retaliation) | Low | Low | Instacart attempted restaurant delivery in 2022 and exited; DoorDash has 67% restaurant market share and 7M Dashers — a 6-year structural moat |
| Cold chain regulatory compliance issues | Low | High | FDA food safety counsel retained; cold chain packaging spec developed with NSF-certified vendor; dark store FSMA compliance built into site design |

# 12. Implementation Timeline

| Phase | Dates | Key Deliverables | Milestone |
| --- | --- | --- | --- |
| Phase 0: Foundation | Q2 2025 (Apr-Jun) | Finalize Kroger/Albertsons partnership agreements; hire 80 grocery product engineers; dark store site selection for top 10 metros | Board approval; retailer LOIs signed |
| Phase 1: Retailer Launch | Q3 2025 (Jul-Sep) | DoorDash Grocery Partner program live in 3,000 Kroger and 2,200 Albertsons stores; inventory API integration; grocery Dasher certification pilot | 5,200 partner stores live; 100K certified Dashers |
| Phase 2: Dark Store & Dasher Scale | Q4 2025 (Oct-Dec) | First 85 dark stores operational in top 40 metros; 400K certified Dashers; DashPass Grocery tier launched; $4.2B grocery GMV run rate | 85 dark stores live; 400K certified Dashers; $4.2B GMV |
| Phase 3: National Scale | Q1-Q3 2026 (Jan-Sep) | Publix and HEB live; AI grocery recommendations in app; DashPass grocery conversion program; $7.8B grocery GMV run rate | 7,000+ partner stores; $7.8B GMV; EBITDA positive |
| Phase 4: Optimize & Expand | Q4 2026 - Q4 2027 | International grocery launch (Canada, Australia); dark store expansion to 200 sites; private-label grocery brand launch on DashMart; $12.5B GMV target | $12.5B grocery GMV; $987M EBITDA; $2.46B revenue |

# 13. Recommendation & Ask

The DoorDash New Verticals Strategy & Product Office recommends that the Executive Review Board approve the following program:

| Ask | Details |
| --- | --- |
| Capital Investment | $671M Year 1 / $726M Year 2 / $765M Year 3 = $2,162M total program budget |
| Headcount Authorization | 380 net new FTEs: 130 engineering & product, 90 operations (dark stores, Dasher ops), 80 retailer partnerships, 80 marketing |
| Decision Requested | Board approval of full 3-year Grocery Vertical program; Q3 2025 kick-off; quarterly GMV and EBITDA reporting to Board |
| Expected Outcome | $12.5B grocery GMV by FY2027; $2.46B platform revenue; $987M EBITDA in Year 3; NPV $968M; IRR 44% |

Grocery is not a nice-to-have for DoorDash — it is the next platform. With 67% restaurant market share and 7M Dashers, DoorDash has the supply-side infrastructure to become the dominant grocery delivery platform in the U.S. The question is not whether to enter grocery at scale; it is whether DoorDash will do so before Instacart fortifies its retail partnerships. We recommend approving the full program immediately.